## Slide 1
PROJECT NAME: TORRENT POWER, NARANPURA
PRESENTED BY:
TPNA Team
PROJECT REVIEW MEETING
HI-TECH PROJECTS PVT. LTD.

## Slide 2
PROJECT REVIEW MEETING JAN'22
PROJECT DETAILS | 
Project | Torrent Power, Naranpura
Client | Torrent Power
Architect | Munjal Bhatt
Structural Consultant | Ducon Consultant Pvt. Ltd.
Consultant | TUV Nord
Tender Cost (in lacs) | 2716.72
Tentative Project Cost (in lacs) | 5500
Start Date (As per PO) | 09/08/2018
Finish Date (As per PO) | 30/10/2022
Actual Start Date | 15/09/2018
Finish Date (As per Bar Chart) | 31/12/2022
Lapsed Vs Total Duration in days | 1257/1569 Days
Project plan Vs Achievement (in lacs) | 3807/3508.03 lacs = 108.52%
Billing Till Last Month (in lacs) | 3807 lacs

## Slide 3
PROJECT REVIEW MEETING JAN'22
REVIEW OF LAST MOM
MOM - PROJECT REVIEW MEETING |  |  |  |  |  | 
SITE |  | TPNA | Date | 28/12/2021 |  | 
Sr. | Agenda Points | Key Measurable / Action to be Taken | Responsible Person | Target Date | Progress Status | Action Taken
1 | Flooring Material | Check data of site infra flooring material. Seems too high in CCR report. | Dipal Patel, Sagar Lodaya, Dhruvil Raval | 31/12/2021 | Done | New labour colony Cement fibre sheet amount of 3.58 lacs.
2 | Machine hiring | Check machine hiring charges on site. Seems too high in CCR report. | Dipal Patel, Sagar Lodaya, Dhruvil Raval | 31/12/2021 | Done | Reduced hiring charges from Nov’21 – 70k to Dec’21 – 48k and in Jan’22 – 26k
3 | PRM Presentation | Add a slide about reason of variance for feasibility vs. achievement. | Dipal Patel, Sagar Lodaya, Dhruvil Raval | 13/01/2022 | Done | Incorporated in slide
4 | Sparing in ERP | Spare the extra material/asset from ERP little in advance to enable more effective material/asset management. | Dipal Patel, Sagar Lodaya, Dhruvil Raval | 29/12/2021 | Done | Balance shuttering material identified
5 | Store | At the end of the month, run closing stock report in ERP and check with physical stock on site with the help of store in-charge for more accurate data. Make it a practice. | Dipal Patel, Sagar Lodaya, Dhruvil Raval | 31/12/2021 | In Progress | In Progress

## Slide 4
Project Value | For the month of January’22 |  |  |  | Cumulative for the Project up January’22 |  | 
 | Sales as per Bar chart | Sales as per Feasibility | Sales (Client Bill) | % Achievement | Cumulative Sales as per Bar chart | Cumulative (Client Bill + WIP) Sales | % Achievement wrt Bar chart
A | B | C | D | E = D/C | F | G | H = G/F
5500 | 111.69 | 100.64 | 154 (81+63+10) (Payable + Exhausted + Extra item) | 153.02% | 3508.03 | 3807 | 108.52%
PLAN V/S ACTUAL
Note: All figures are in Lacs
PROJECT REVIEW MEETING JAN'22

## Slide 5
Sr. No. | Description | Unit | Feasibility Plan |  | Achievement |  | Remarks
 |  |  | Qty | Amount (lacs) | Qty | Amount(lacs) | 
1 | Reinforcement | MT | 67.58 | 43.54 | 74.91 | 48.26 | 6FRS Pour 2, 7FRS Pour 1 & 2, 4FRS Pour 4
2 | Shuttering | Sqm | 1883.18 | 17.49 | 2434.89 | 21.85 | 6FRS Pour 2, 7FRS Pour 1 & 2, 4FRS Pour 4, GF to 4F Lintel
3 | Concrete | Cum | 356.90 | 21.03 | 410.48 | 23.91 | 6FRS Pour 2, 7FRS Pour 1 & 2, 4FRS Pour 4
4 | Blockwork | Cum | 217.10 | 11.25 | 546.26 | 28.72 | 2nd,3rd,4th Floor
5 | Plaster | Sqm | 1632 | 5.58 | 2186 | 7.47 | GF & 1st Floor
6 | Other |  |  | 1.74 |  | 24.7 | Extra Item – 10.01 Lacs
Total |  |  |  | 100.63 |  | 154.84 | 
REASON OF VARIANCE
PROJECT REVIEW MEETING JAN'22

## Slide 6
NEXT QUARTER PLAN
Project Value (in lacs) | Cumulative Bill Achieved up to previous month | % Completed | Next Quarter Plan (in lacs) |  |  | Quarter's Target | Balance Amount | Remarks
 |  |  | Feb-22 | Mar-22 | Apr-22 |  |  | 
A | B | C = B/A | D | E | F | G = D+E+F | H = A - (B+G) | 
5500 | 3807 | 69.22% | 98.05 | 125 | 124 | 347.05 | 1345.95 | As per last budget
PROJECT REVIEW MEETING JAN'22
Note: All figures are in Lacs

## Slide 7
PROJECT REVIEW MEETING JAN'22
MANPOWER STATUS
Group Name | Manpower Requirement for Feb’22 |  |  | Total Available in Feb’22 | Shortfall
 | Skilled | Unskilled | Total |  | 
A | B | C | D=B+C | E | F=D-E
Reinforcement | 13 | 13 | 26 | 15 | 11
Formwork | 15 | 15 | 30 | 26 | 4
Post Tension | 1 | 1 | 2 | 0 | 2
Rebar | 1 | 0 | 1 | 1 | 0
Unskilled | 4 | 30 | 34 | 27 | 7
Hacking Work | 0 | 2 | 2 | 0 | 2
Painting | 2 | 2 | 4 | 6 | -2
Rendering | 1 | 1 | 2 | 0 | 2
Trimix Work | 0 | 0 | 0 | 0 | 0
Flooring Work | 2 | 2 | 4 | 9 | -5

## Slide 8
PROJECT REVIEW MEETING JAN'22
MANPOWER STATUS
Group Name | Manpower Requirement for Feb’22 |  |  | Total Available in Feb’22 | Shortfall
 | Skilled | Unskilled | Total |  | 
A | B | C | D=B+C | E | F=D-E
Waterproofing Work | 1 | 1 | 2 | 0 | 2
Fabrication Work | 0 | 0 | 0 | 0 | 0
False Ceiling Work | 0 | 0 | 0 | 0 | 0
Masonry & Plaster Work | 15 | 22 | 37 | 39 | -2
POP Punning | 2 | 3 | 5 | 5 | 0
Doors and Window | 0 | 0 | 0 | 0 | 0
Plumbing | 2 | 2 | 4 | 2 | 2
Total Manpower | 59 | 94 | 153 | 130 | 23

## Slide 9
PROJECT REVIEW MEETING JAN'22
Category Name | Nov-21 | Dec-21 | Jan-22
Consumable Asset | 10.43 | 10.64 | 10.55
Material | 36.37 | 34.19 | 55.97
Oil & Fuel | 0.23 | 0.23 | 0.40
Sparepart | 0.98 | 0.97 | 0.95
Total | 48.01 | 46.03 | 67.87
Note: All figures are in Lacs
LAST 3 MONTH VALUATION

## Slide 10
PROJECT CURRENT STATUS PHOTOS
PROJECT REVIEW MEETING JAN'22
PSC Building

## Slide 11
PROJECT CURRENT STATUS PHOTOS
PROJECT REVIEW MEETING JAN'22
PSC Building

## Slide 12
PROJECT CURRENT STATUS PHOTOS
PROJECT REVIEW MEETING JAN'22
MTL Building

## Slide 13
PSC BUILDING - PICTORIAL PROGRESS
PROJECT REVIEW MEETING JAN'22
PSC Building Progress status – 15.02.22
Pour 2 – 8FRS - Slab R/F in Progress
Pour 1 – 8FRS - Slab R/F in progress
Pour 3 – 5FRS -Slab completed
PSC Building Plan Area
GF
1st
7th
10th
9th
8th
3rd
4th
5th
6th
2nd
Legends
Slab Work Balance
Slab in progress
Slab Completed
B/W & Plaster WIP
POP Punning WIP
POP Punning Completed

## Slide 14
SUPPORT FROM HEAD OFFICE
PROJECT REVIEW MEETING JAN'22